## Sheet1
Sprint Retrospective
| What went well | What went poorly | What ideas do you have | How should we take action
| This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints.
Sprint 1 – Data Preparation | Dataset loading and preprocessing completed successfully. Data cleaning and encoding were effective. | Handling missing values took more time than expected. | Use automated preprocessing techniques. | Apply efficient imputation methods and preprocessing pipelines.
Sprint 2 – Model Development | Model training completed with good accuracy. Evaluation metrics generated successfully. | Initial model accuracy was low. | Improve model performance using tuning. | Apply feature selection and hyperparameter tuning.
Sprint 3 – Multi-Agent System | Multi-agent modules implemented successfully. Bias detection and explainability achieved. | Integration of multiple agents was complex. | Use modular architecture for agents. | Improve communication between agents using structured APIs.
Sprint 4 – Integration & Testing | Compliance reports generated successfully. Dashboard displayed results clearly. | UI development took extra time. | Simplify UI design for better usability. | Optimize UI and improve visualization components.